## Sheet1
Task | Start Date | Duration | End Date
Add Payment feature with PayPal | 2014-04-01 | 1 | 2014-05-06
Add User Authentication and Security | 2014-03-25 | 2 | 2014-05-06
Setup PostGreSQL Database Server | 2014-03-18 | 2 | 2014-05-06
Setup the back- end, HTTP Server | 2014-02-11 | 3 | 2014-05-06
Develop Front- End Application with Basic Template and Functionality | 2014-01-28 | 5 | 2014-05-06